## RTM
Switchr - Requirements Traceability Matrix - CSE 4214 Sprint 3
Req ID | Req Description | Relevant User Story ID | Relevant Issues | Relevant Test Cases | Tests Passing/Failing
REQ-1 | The system shall provide a registration form accessible from the homepage. | US-1 | #56 | Integration_Testing/test_auth.py | 15/15
REQ-2 | The system shall require users to enter a valid email address for account creation. | US-1 | #56 | Integration_Testing/test_auth.py | 15/15
REQ-3 | The system shall require users to create a unique username for account creation. | US-1 | #56 | Integration_Testing/test_auth.py | 15/15
REQ-4 | The system shall require users to create a password that meets minimum strength requirements. | US-1 | #56 | Integration_Testing/test_auth.py | 15/15
REQ-5 | The system shall create a new user account upon successful validation. | US-1 | #56 | Integration_Testing/test_auth.py | 15/15
REQ-6 | The system shall send a confirmation email upon successful registration. | US-1 | #56 | Integration_Testing/test_auth.py | 15/15
REQ-7 | The system shall display a success message after account creation. | US-1 | #56 | Integration_Testing/test_auth.py | 15/15
REQ-8 | The system shall provide a login form accessible from the homepage. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-9 | The system shall allow users to log in using a valid email address or username and password combination. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-10 | The system shall validate user credentials against stored account data before granting access. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-11 | The system shall verify that all required login fields are not empty before submission. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-12 | The system shall validate the format of the email input when email is used for login. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-13 | The system shall not allow a user to log in with incorrect credentials and shall display an appropriate error message. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-14 | The system shall not indicate which specific field is incorrect to prevent security risks. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-15 | The system shall create an authenticated user session upon successful login. | US-2 | #52, #67 | Integration_Testing/test_auth.py | 15/15
REQ-16 | The system shall maintain the user session across pages until the user logs out or the session expires. | US-2 | #67 | Integration_Testing/test_auth.py | 15/15
REQ-17 | The system shall restrict access to protected pages and features to authenticated users only. | US-2 | #67 | Integration_Testing/test_auth.py | 15/15
REQ-18 | The system shall provide a Forgot Password option on the login form. | US-2 | #57 | Not implemented | N/A
REQ-19 | The system shall send a password reset link to the users registered email upon request. | US-2 | #57 | Not implemented | N/A
REQ-20 | The system shall terminate the user session upon logout. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-21 | The system shall redirect the user to the homepage after logout. | US-2 | #52 | Integration_Testing/test_auth.py | 15/15
REQ-22 | The system shall provide a My Profile section for logged-in users. | US-3 | #58 | Not implemented | N/A
REQ-23 | The system shall display current profile information (username, email, bio, profile photo). | US-3 | #58 | Not implemented | N/A
REQ-24 | The system shall allow users to update profile information (username, email, bio, profile photo). | US-3 | #58 | Not implemented | N/A
REQ-25 | The system shall allow users to update their email address and passwords. | US-3 | #58 | Not implemented | N/A
REQ-26 | The system shall provide a Create Listing option to logged-in users. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-27 | The system shall require a title for each listing (maximum 100 characters). | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-28 | The system shall require a description for each listing. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-29 | The system shall require the user to select a category. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-30 | The system shall require the user to select item condition. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-31 | The system shall require the user to enter an asking price or estimated trade value. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-32 | The system shall require the user to select a listing type: for sale, for trade, or both. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-33 | The system shall allow the user to upload at least one photo. | US-4 | #84 | Integration_Testing/test_listings.py | 18/18
REQ-34 | The system shall save the listing and assign it a unique listing ID. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-35 | The system shall set the listing status to active upon successful creation. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-36 | The system shall make the listing visible on the browse page immediately after creation. | US-4 | #66 | Integration_Testing/test_listings.py | 18/18
REQ-37 | The system shall provide an Edit option for each listing owned by the logged-in user. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-38 | The system shall display the current listing data in an editable form. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-39 | The system shall allow the user to edit the listing title. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-40 | The system shall allow the user to edit the listing description. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-41 | The system shall allow the user to change the category. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-42 | The system shall allow the user to change the item condition. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-43 | The system shall allow the user to update the asking price or trade value. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-44 | The system shall allow the user to change the listing type. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-45 | The system shall validate all edited fields using the same rules as listing creation. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-46 | The system shall save changes and update the listing upon successful validation. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-47 | The system shall not allow editing of listings with completed transaction status. | US-5 | #65 | Integration_Testing/test_listings.py | 18/18
REQ-48 | The system shall provide a Delete option for each listing owned by the logged-in user. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-49 | The system shall display a confirmation prompt before deleting a listing. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-50 | The system shall remove the listing from the marketplace upon user confirmation. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-51 | The system shall delete all associated photos when a listing is removed. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-52 | The system shall cancel any pending offers associated with the deleted listing. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-53 | The system shall notify users with pending offers that the listing has been removed. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-54 | The system shall display a success message after deletion. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-55 | The system shall not allow users to delete listings they do not own. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-56 | The system shall not allow deletion of listings with an active transaction in progress. | US-6 | #74 | Integration_Testing/test_listings.py | 18/18
REQ-57 | The system shall display all active listings on the browse page. | US-7 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-58 | The system shall display listing thumbnail, title, price, and condition in the browse view. | US-7 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-59 | The system shall indicate whether a listing is for sale, for trade, or both. | US-7 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-60 | The system shall sort listings by most recently posted by default. | US-7 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-61 | The system shall implement pagination or infinite scroll for large listing sets. | US-7 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-62 | The system shall allow users to click on a listing to view full details. | US-7 | #73, #75 | Integration_Testing/test_listings.py | 18/18
REQ-63 | The system shall display full listing details including all photos, description, seller info, and listing type. | US-7 | #73, #75 | Integration_Testing/test_listings.py | 18/18
REQ-64 | The system shall allow browsing without requiring user login. | US-7 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-65 | The system shall provide filter options on the browse page. | US-8 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-66 | The system shall allow filtering by categories. | US-8 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-67 | The system shall allow filtering by condition. | US-8 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-68 | The system shall allow filtering by listing type. | US-8 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-69 | The system shall allow filtering by price range. | US-8 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-70 | The system shall update the listing display in real-time as filters are applied. | US-8 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-71 | The system shall display the number of listings that match the current filter. | US-8 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-72 | The system shall provide a Clear Filter option to reset all filters. | US-8 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-73 | The system shall provide a search bar accessible from all pages. | US-9 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-74 | The system shall search listing titles for matching keywords. | US-9 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-75 | The system shall search listing descriptions for matching keywords. | US-9 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-76 | The system shall display search results ranked by relevance. | US-9 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-77 | The system shall display the number of results found. | US-9 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-78 | The system shall display a No results found message when no listings match. | US-9 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-79 | The system shall allow filters to be applied to search results. | US-9 | #75 | Integration_Testing/test_listings.py | 18/18
REQ-80 | The system shall display a Buy option on listings marked for sale or both. | US-10 | #73 | Integration_Testing/test_purchase.py | 11/11
REQ-81 | The system shall require users to be logged in to initiate a purchase. | US-10 | #72, #73 | Integration_Testing/test_purchase.py | 11/11
REQ-82 | The system shall display the listing price and any applicable details before purchase confirmation. | US-10 | #73 | Integration_Testing/test_purchase.py | 11/11
REQ-83 | The system shall allow the buyer to confirm or cancel the purchase before submitting. | US-10 | #72, #73 | Integration_Testing/test_purchase.py | 11/11
REQ-84 | The system shall provide a simulated payment process. | US-10 | #73 | Integration_Testing/test_purchase.py | 11/11
REQ-85 | The system shall not process real financial transactions (simulation only). | US-10 | #73 | Integration_Testing/test_purchase.py | 11/11
REQ-86 | The system shall mark the listing status as sold upon completed transaction. | US-10 | #73 | Integration_Testing/test_purchase.py | 11/11
REQ-87 | The system shall remove the listing from active browser results after sale. | US-10 | #73 | Integration_Testing/test_purchase.py | 11/11
REQ-88 | The system shall record the transaction in both buyer and seller history. | US-10 | #73 | Integration_Testing/test_purchase.py | 11/11
REQ-89 | The system shall not allow users to purchase their own listings. | US-10 | #72 | Integration_Testing/test_purchase.py | 11/11
REQ-90 | The system shall display an Offer Trade option on listings marked for trade or both. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-91 | The system shall require users to be logged in to initiate a trade. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-92 | The system shall require the trader to have at least one active listing to propose a trade. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-93 | The system shall display a trade proposal form showing the desired item. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-94 | The system shall allow the trader to select one or more of their own listings to offer. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-95 | The system shall allow the trader to add simulated cash to balance an uneven trade. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-96 | The system shall allow the trader to submit the trade offer. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-97 | The system shall notify the seller of the incoming trade offer. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-98 | The system shall display all trade offer details to the seller. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-99 | The system shall allow the seller to accept the trade offer. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-100 | The system shall allow the seller to reject the trade offer. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-101 | The system shall allow the seller to counter the trade offer with different terms. | US-11 | #79 | Not implemented | N/A
REQ-102 | The system shall notify the trader when the seller responds. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-103 | The system shall mark both listings as traded upon accepted trade. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-104 | The system shall remove both listings from active browse results after trade. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-105 | The system shall record the transaction in both users trade history. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-106 | The system shall not allow users to trade with themselves. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-107 | The system shall allow either party to cancel a pending trade offer before acceptance. | US-11 | #79 | Integration_Testing/test_trade.py | 14/14
REQ-108 | The system shall provide an Offers or My Offers section for logged-in users. | US-12 | #59, #60 | Not implemented | N/A
REQ-109 | The system shall display all incoming offers on the users listings. | US-12 | #59 | Not implemented | N/A
REQ-110 | The system shall display all outgoing offers the user has made. | US-12 | #59 | Not implemented | N/A
REQ-111 | The system shall show offer status (pending, accepted, rejected, countered, expired). | US-12 | #59 | Not implemented | N/A
REQ-112 | The system shall display offer details including items, value, and any cash added. | US-12 | #60 | Not implemented | N/A
REQ-113 | The system shall allow sellers to accept an offer. | US-12 | #59 | Not implemented | N/A
REQ-114 | The system shall allow sellers to reject an offer. | US-12 | #59 | Not implemented | N/A
REQ-115 | The system shall allow buyers/traders to accept or reject counter-offers. | US-12 | #59 | Not implemented | N/A
REQ-116 | The system shall allow buyers/traders to counter a counter-offer. | US-12 | #59 | Not implemented | N/A
REQ-117 | The system shall allow either party to cancel a pending offer. | US-12 | #59 | Not implemented | N/A
REQ-118 | The system shall automatically expire offers after a set time period. | US-12 | #59 | Not implemented | N/A
REQ-119 | The system shall allow sellers to manage multiple offers on the same listing. | US-12 | #59 | Not implemented | N/A
REQ-120 | The system shall automatically reject other pending offers when one is accepted. | US-12 | #59 | Not implemented | N/A
REQ-121 | The system shall prevent actions on offers for listings that are no longer active. | US-12 | #59 | Not implemented | N/A
REQ-122 | The system shall provide a History section for logged-in users. | US-13 | #61 | Integration_Testing/test_history.py | 9/9
REQ-123 | The system shall display the users past purchases. | US-13 | #61 | Integration_Testing/test_history.py | 9/9
REQ-124 | The system shall display the users past sales. | US-13 | #61 | Integration_Testing/test_history.py | 9/9
REQ-125 | The system shall display the users past trades. | US-13 | #61 | Integration_Testing/test_history.py | 9/9
REQ-126 | The system shall sort history by most recent by default. | US-13 | #61 | Integration_Testing/test_history.py | 9/9
REQ-127 | The system shall allow administrators to log in with admin credentials. | US-14 | #67 | Integration_Testing/test_admin.py | 13/13
REQ-128 | The system shall restrict admin functionality to users with administrative privileges. | US-14 | #67 | Integration_Testing/test_admin.py | 13/13
REQ-129 | The system shall allow administrators to view all registered users. | US-14 | #68 | Integration_Testing/test_admin.py | 13/13
REQ-130 | The system shall allow administrators to view all listings in the system. | US-14 | #68 | Integration_Testing/test_admin.py | 13/13
REQ-131 | The system shall allow administrators to remove or deactivate user accounts. | US-14 | #68 | Integration_Testing/test_admin.py | 13/13
REQ-132 | The system shall allow administrators to remove or deactivate listings that violate system guidelines. | US-14 | #68 | Integration_Testing/test_admin.py | 13/13
REQ-133 | The system shall allow administrators to view system activity such as listings, transactions, and user interactions. | US-14 | #68 | Integration_Testing/test_admin.py | 13/13
REQ-134 | The system shall log administrative actions for traceability. | US-14 | #68 | Integration_Testing/test_admin.py | 13/13
REQ-135 | The system shall not require administrator approval for new user account creation. | US-14 | #67 | Integration_Testing/test_admin.py | 13/13
REQ-136 | The system shall not require administrator approval for new listings to be posted. | US-14 | #66 | Integration_Testing/test_admin.py | 13/13
REQ-137 | The system shall provide a Report option on all listings. | US-15 | #62 | Not implemented | N/A
REQ-138 | The system shall provide a Report option on all user profiles. | US-15 | #62 | Not implemented | N/A
REQ-139 | The system shall require users to be logged in to submit a report. | US-15 | #62 | Not implemented | N/A
REQ-140 | The system shall display a report form with reason options. | US-15 | #62 | Not implemented | N/A
REQ-141 | The system shall allow users to add optional details or comments to the report. | US-15 | #62 | Not implemented | N/A
REQ-142 | The system shall log the report with timestamp, reporter, and reported content. | US-15 | #62 | Not implemented | N/A
REQ-143 | The system shall add the report to the admin moderation queue. | US-15 | #62 | Not implemented | N/A
REQ-144 | The system shall allow admins to view all pending reports. | US-15 | #62 | Not implemented | N/A
REQ-145 | The system shall allow admins to mark reports as reviewed. | US-15 | #62 | Not implemented | N/A
REQ-146 | The system shall allow admins to dismiss reports with no action. | US-15 | #62 | Not implemented | N/A
REQ-153 | The system shall allow buyers to view completed purchases in their order history. | US-16 | #82 | Integration_Testing/test_history.py | 9/9
REQ-154 | The system shall provide a Request Return option for eligible completed purchases. | US-16 | #82 | Integration_Testing/test_history.py | 9/9
REQ-155 | The system shall require buyers to select a reason when submitting a return request. | US-16 | #82 | Integration_Testing/test_history.py | 9/9
REQ-156 | The system shall notify the seller when a return request is submitted. | US-16 | #82 | Integration_Testing/test_history.py | 9/9
REQ-157 | The system shall allow sellers to accept or reject return requests. | US-16 | #82 | Not implemented | N/A
REQ-158 | The system shall update the order status based on the sellers decision. | US-16 | #82 | Not implemented | N/A
REQ-159 | The system shall process a simulated refund when a return is accepted. | US-16 | #82 | Not implemented | N/A
REQ-160 | The system shall notify the buyer of the sellers decision. | US-16 | #82 | Not implemented | N/A